## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Theorie | 5 | 2025-07-01 | Learning about how to make maze, maze algorithm, jobs system, performance, making complete plan with deadline, setting trello and git ready.
Getting started | 3.5 | 2025-07-01 | To make sure I learned the theory well, I had to test it. So I made a simple maze system using two types of algorithms: Prim's and Drunken Brawl. Then I tested and debugged everything to ensure I understood every single step not just implement it and suddenly have a maze. I wanted to understand every single step so that later I would know how to create my own design. In the maze scene, you can see what I have achieved from learning the theory and implementing it. Bear in mind, I haven’t focused on comments or best practices this was purely for demonstration purposes.
UML design and thinking about the overall design process. | 0.5 | 2025-07-02 | To ensure my architecture is solid, I created a simple UML diagram to visually understand what I need and how it’s going to work.
Maze Generator | 2 | 2025-07-02 | To build a reusable, solid Maze Generator script, it required not just a single implementation but also debugging and ensuring that dictionary/lists were passed correctly to other scripts. So yes, taking time to build something that may seem simple like a generator but designing it to be well decoupled is really important for future use.
MazeGridPoolManager | 0.2 | 2025-07-02 | Pool manager script makes sure turn on/off all cubes that are in Dictionary.
MazeDictMeshRenderer | 1 | 2025-07-02 | This script is designed to toggle rendering on and off using batching for better performance. Without it, rendering 62,500 objects at once would overwhelm Unity.
MazeRenderCulling | 2 | 02/072025 | I implemented MazeRenderCulling so that when I add the player later, they can move without experiencing performance issues. The reason it took some times I had to look up what is the best for preformance.
Run Time Resizing | 3 | 2025-07-02 | To ensure smooth and performance-friendly resizing at runtime, I implemented it using Unity's Job System. This allows the process to run in parallel across multiple threads, rather than relying on just one. It took some time, as I was familiar with what the Job System does but had never used it before this was a great opportunity to learn and apply it.
Utility class | 4 | 2025-07-03 | This utility class contains functions that each have their own specific responsibility. These core functions are used throughout the project.
Prim's Algorithm First & Second approach | 3 | 2025-07-03 | Using all my previous structural implementations, I combined them to create a maze with a step by step animation and a highly customizable algorithm.
Build The user interface | 4 | 2025-07-04 | This is where I built the dialogue text for the tutorial. I linked almost every script and implemented User Story 4, which focuses on screen resolution. I also handled debugging and testing to make sure everything works properly through the UI.
Optioanl area:
MazeCameraController | 0.5 | 2025-07-04
FreeCameraController | 1 | 2025-07-04 | This script allows the user to control the camera similar to Unity scene camera, but with some limitations
PlayerMovement | 1 | 2025-07-04 | Simplist playermovent ever but it had to be linked with camera it took bit coz of testing too.
Post processing | 0.5 | 2025-07-04 | Implemented a dark theme that suits the maze and its environment.
Debugging, trouble shooting, looking up something etc | 5 |  | To be as honest as possible, I sometimes had to test things, fix issues, and look up solutions or watch tutorial videos. And yes, I had a drink or two along the way. Including all of that, the total time spent was approximately five hours across the total time of project.
documenting the code architecture | 1.5 | 2025-07-04 | Made world documents that includes code architecture and what is good in the implementation I did.
Total amount of hours | 32